## Tabelle1
Date | Descrition | Workhours | Name
2021-12-04 | Basicmovement, Cameracontrol | 3 | Sarvan Amel
2021-12-05 | Initialcontroles, Keybindings | 3 | Kern Philip
| Pickup items | 3 | Lasinger Christoph
2021-12-06 | Tested picking up items | 2 | Lasinger Christoph
| Tried to improve picking up items | 2 | Sarvan Amel
Name | Total workhours
Kern Philip | 3
Lasinger Christoph | 5
Sarvan Amel | 5
13
Date | Descrition | Workhours | Name
2021-12-13 | Wrote ReadMe file | 2 | Lasinger Christoph
| Created and edited first Hugo landing page | 2 | Sarvan Amel
| Created and edited Hugo landing page | 1.5 | Kern Philip
2021-12-15 | Tried to create Hugo landing page on oracle vm | 1 | Lasinger Christoph
| Tried to make landing page accessible | 1 | Kern Philip
| Tried to create landing page on vm | 1 | Sarvan Amel
2021-12-19 | Made landing page accessible | 2 | Kern Philip
| Created Hugo landing page on oracle vm | 2 | Lasinger Christoph
| Tried to edit content on landing page | 2 | Sarvan Amel
Name | Total workhours
Kern Philip | 4.5
Lasinger Christoph | 5
Sarvan Amel | 5
14.5
Date | Descrition | Workhours | Name
2021-12-20 | Created a better time record | 0.7 | Sarvan Amel
| Creating ERD | 1.5 | Sarvan Amel
Sprint 1
Sprint 1
Sprint 1
Sprint 1
Sprint 2
Sprint 3